## CR-05 - Goals and Outcomes

Progress the jurisdiction has made in carrying out its strategic plan and its action plan.  91.520(a)

This could be an overview that includes major initiatives and highlights that were proposed and executed throughout the program year.

We provided $154,000 in HOME funds for down payment assistance to four first time homebuyers. These first-time homebuyers purchased newly constructed homes developed by a local non-profit developer. The housing market is still challenging. Properties are still selling very quickly with multiple offers over asking price. Home prices have dramatically increased which has made it very challenging to be a first-time homebuyer. A pending soft commitment of $850,000 in HOME funds was made to support a funding application for the development of 150 units of rental housing at the Marriner Mill. This project has not started construction yet as it is still pulling together all financing. Another pending soft commitment of $1,000,000 in HOME funds was made to support a funding application for the development of 98 units of affordable rental housing at 59-71 Merrimack Street. This project has not started construction yet as it is still pulling together all financing. The Stone Mill has fully leased up the 86 units and a ribbon cutting was held. Island Parkside Phase II (now known as the Armand Michael Hyatt Apartments) also has fully leased up the 40 units and held a ribbon cutting.  Since many non-profit organizations received ARPA/Free Cash funding from the City for FY24-FY25 through the Creating a Thriving Lawrence Program, the Mayor decided not to fund any public service activities except for the ongoing commitment to Emmaus.   CDBG funds were used to defease the last note on the City’s Section 108 loan. By doing this, the City has freed up future Program Year CDBG funds that would have been needed to make the semi-annual loan payments.

Comparison of the proposed versus actual outcomes for each outcome measure submitted with the consolidated plan and explain, if applicable, why progress was not made toward meeting goals and objectives.  91.520(g)

Categories, priority levels, funding sources and amounts, outcomes/objectives, goal outcome indicators, units of measure, targets, actual outcomes/outputs, and percentage completed for each of the grantee’s program year goals.

| Goal | Category | Source / Amount | Indicator | Unit of Measure | Expected – Strategic Plan | Actual – Strategic Plan | Percent Complete | Expected – Program Year | Actual – Program Year | Percent Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Affordable Housing | Affordable Housing Homeless | CDBG: $ / HOPWA: $0 / HOME: $ / ESG: $0 | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 0 | 3 |  |  |  |  |
| Affordable Housing | Affordable Housing Homeless | CDBG: $ / HOPWA: $0 / HOME: $ / ESG: $0 | Rental units constructed | Household Housing Unit | 0 | 27 |  | 11 | 22 | 200.00% |
| Affordable Housing | Affordable Housing Homeless | CDBG: $ / HOPWA: $0 / HOME: $ / ESG: $0 | Rental units rehabilitated | Household Housing Unit | 150 | 72 | 48.00% | 0 | 7 |  |
| Affordable Housing | Affordable Housing Homeless | CDBG: $ / HOPWA: $0 / HOME: $ / ESG: $0 | Homeowner Housing Added | Household Housing Unit | 4 | 5 | 125.00% |  |  |  |
| Affordable Housing | Affordable Housing Homeless | CDBG: $ / HOPWA: $0 / HOME: $ / ESG: $0 | Homeowner Housing Rehabilitated | Household Housing Unit | 73 | 103 | 141.10% | 12 | 12 | 100.00% |
| Affordable Housing | Affordable Housing Homeless | CDBG: $ / HOPWA: $0 / HOME: $ / ESG: $0 | Direct Financial Assistance to Homebuyers | Households Assisted | 65 | 4 | 6.15% |  |  |  |
| Affordable Housing | Affordable Housing Homeless | CDBG: $ / HOPWA: $0 / HOME: $ / ESG: $0 | Homelessness Prevention | Persons Assisted | 0 | 1 |  |  |  |  |
| Affordable Housing | Affordable Housing Homeless | CDBG: $ / HOPWA: $0 / HOME: $ / ESG: $0 | Housing for Homeless added | Household Housing Unit | 0 | 0 |  | 0 | 0 |  |
| Affordable Housing | Affordable Housing Homeless | CDBG: $ / HOPWA: $0 / HOME: $ / ESG: $0 | Housing for People with HIV/AIDS added | Household Housing Unit | 0 | 0 |  | 0 | 0 |  |
| Economic Development | Non-Homeless Special Needs Non-Housing Community Development | CDBG: $ | Facade treatment/business building rehabilitation | Business | 3 | 0 | 0.00% |  |  |  |
| Economic Development | Non-Homeless Special Needs Non-Housing Community Development | CDBG: $ | Jobs created/retained | Jobs | 0 | 4 |  |  |  |  |
| Economic Development | Non-Homeless Special Needs Non-Housing Community Development | CDBG: $ | Businesses assisted | Businesses Assisted | 22 | 4 | 18.18% |  |  |  |
| Homeless Services | Homeless | CDBG: $ / ESG: $ | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 10 | 14 | 140.00% |  |  |  |
| Homeless Services | Homeless | CDBG: $ / ESG: $ | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 10 | 0 | 0.00% |  |  |  |
| Homeless Services | Homeless | CDBG: $ / ESG: $ | Homelessness Prevention | Persons Assisted | 10 | 23 | 230.00% | 14 | 0 | 0.00% |
| Planning and Admin | Affordable Housing Homeless Non-Homeless Special Needs Non-Housing Community Development | CDBG: $ / HOPWA: $0 / HOME: $ / ESG: $ | Other | Other | 1 | 1 | 100.00% | 1 | 0 | 0.00% |
| Public Infrastructure, Facilities, and Parks | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 200 | 286551 | 143,275.50% | 70000 | 77850 | 111.21% |
| Public Infrastructure, Facilities, and Parks | Non-Housing Community Development | CDBG: $ | Other | Other | 1 | 0 | 0.00% |  |  |  |
| Public Services | Homeless Non-Homeless Special Needs | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 0 | 0 |  |  |  |  |
| Public Services | Homeless Non-Homeless Special Needs | CDBG: $ | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 900 | 818 | 90.89% |  |  |  |
| Rental Assistance | Homeless Households impacted by COVID 19 | HOME: $ | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 50 | 0 | 0.00% |  |  |  |

Table 1 - Accomplishments – Program Year & Strategic Plan to Date

Assess how the jurisdiction’s use of funds, particularly CDBG, addresses the priorities and specific objectives identified in the plan, giving special attention to the highest priority activities identified.

Funds were allocated in alignment with the priorities identified in the consolidated and annual action plan. These included park and infrastructure improvements, public services, economic development, lead abatement and housing rehabilitation, homeownership and housing development. CDBG or HOME funds were used in these projects to support our efforts to meet HUD’s mandate and improve housing accessibility and affordability, and the overall quality of life for the low-to-moderate income residents. Housing development will be counted upon completion of projected construction.

## CR-10 - Racial and Ethnic composition of families assisted

Describe the families assisted (including the racial and ethnic status of families assisted). 91.520(a)

| Describe the clients assisted (including the racial and/or ethnicity of clients assisted with ESG) |  |
| --- | --- |
|  | HESG |
| American Indian, Alaska Native, or Indigenous | 0 |
| Asian or Asian American | 0 |
| Black, African American, or African | 0 |
| Hispanic/Latina/e/o | 0 |
| Middle Eastern or North African | 0 |
| Native Hawaiian or Pacific Islander | 0 |
| White | 0 |
| Multiracial | 0 |
| Client doesn't know | 0 |
| Client prefers not to answer | 0 |
| Data not collected | 0 |
| Total | 0 |

Table 2 – Table of assistance to racial and ethnic populations by source of funds

Narrative

The majority of our program participants identify as "other multi-racial," and that category does not appear on the first chart.  This results in the under-reporting of our program participants under the Race category under both the CDBG and the HOME program. Under CDBG, 43 of the clients in the program year selected other multi-racial. Under Home, 13 clients selected other multi-racial.  Four listed under HOME are down-payment assistance and 9 are rental housing development.

## CR-15 - Resources and Investments 91.520(a)

Identify the resources made available

| Source of Funds | Source | Resources Made Available | Amount Expended During Program Year |
| --- | --- | --- | --- |
| CDBG | public - federal | 2,458,794 | 1,197,833 |
| HOME | public - federal | 1,744,213 | 149,499 |
| HOPWA | public - federal | 0 | 0 |
| ESG | public - federal | 0 | 0 |

Table 3 - Resources Made Available

Narrative

Identify the geographic distribution and location of investments

| Target Area | Planned Percentage of Allocation | Actual Percentage of Allocation | Narrative Description |
| --- | --- | --- | --- |

Table 4 – Identify the geographic distribution and location of investments

Narrative

The allocation of CDBG resources is targeted to best meet the priority needs of low and moderate income persons based on a variety of planning studies and community input in the preceding years.

As stated in the Consolidated Plan and one-year Action Plan, there are no targeted areas. All LMI areas of the City, and LMI households in the one non-LMI Census Tract, benefit from CDBG and HOME funds. For park improvement projects we use the most recently state approved Open Space and Recreation Plan (OSRP) mandated by the Commonwealth. The most recently developed OSRP covers the period of 2017—2024. For our housing programs we emphasize neighborhood revitalization in our review of projects. Our support of the HUD-funded Lead Program with CDBG is based on LMI households with children under 6 in the household and the presence of lead.

Leveraging

Explain how federal funds  leveraged additional resources (private, state and local funds), including a description of how matching requirements were satisfied, as well as how any publicly owned land or property located within the jurisdiction that were used to address the needs identified in the plan.

- $10,000 in CDBG leveraged $242,541 in McKinney-Vento homeless grant for leased scattered site housing. Our CDBG dollars go toward case management.

- $154,000 in HOME funds leveraged $9,04,550 in mortgages for 4 moderate -income families served through our First-time Homebuyer’s Program.

- $1,655,872 in HOME funds leveraged $99,394664.53 in public and private funds to create 126 units of rental housing. Eighty-two are <60% AMI and twenty-seven are 0-30% AMI. Seventeen are market rate. Twenty-two units are HOME units.

- Per the PR-33 report, the City has no match liability for the Program Year.

- During the Program Year, no publicly owned land was sold.

| Fiscal Year Summary – HOME Match |  |
| --- | --- |
| 1. Excess match from prior Federal fiscal year | 0 |
| 2. Match contributed during current Federal fiscal year | 0 |
| 3. Total match available for current Federal fiscal year (Line 1 plus Line 2) | 0 |
| 4. Match liability for current Federal fiscal year | 0 |
| 5. Excess match carried over to next Federal fiscal year (Line 3 minus Line 4) | 0 |

Table 5 – Fiscal Year Summary - HOME Match Report

| Match Contribution for the Federal Fiscal Year |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project No. or Other ID | Date of Contribution | Cash (non-Federal sources) | Foregone Taxes, Fees, Charges | Appraised Land/Real Property | Required Infrastructure | Site Preparation, Construction Materials, Donated labor | Bond Financing | Total Match |
| n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

Table 6 – Match Contribution for the Federal Fiscal Year

HOME MBE/WBE report

| Program Income – Enter the program amounts for the reporting period |  |  |  |  |
| --- | --- | --- | --- | --- |
| Balance on hand at begin-ning of reporting period $ | Amount received during reporting period $ | Total amount expended during reporting period $ | Amount expended for TBRA $ | Balance on hand at end of reporting period $ |
| 40,121 | 46,999 | 40,121 | 0 | 46,999 |

Table 7 – Program Income

Minority Business Enterprises and Women Business Enterprises – Indicate the number and dollar value of contracts for HOME projects completed during the reporting period

|  | Total | Minority Business Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |

| Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |

| Sub-Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

|  | Total | Women Business Enterprises | Male |
| --- | --- | --- | --- |

| Contracts |  |  |  |
| --- | --- | --- | --- |
| Dollar Amount | 0 | 0 | 0 |
| Number | 0 | 0 | 0 |

| Sub-Contracts |  |  |  |
| --- | --- | --- | --- |
| Number | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 |

Table 8 - Minority Business and Women Business Enterprises

Minority Owners of Rental Property – Indicate the number of HOME assisted rental property owners and the total amount of HOME funds in these rental properties assisted

|  | Total | Minority Property Owners |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

Table 9 – Minority Owners of Rental Property

Relocation and Real Property Acquisition – Indicate the number of persons displaced, the cost of relocation payments, the number of parcels acquired, and the cost of acquisition

|  | Number | Cost |
| --- | --- | --- |
| Parcels Acquired | 0 | 0 |
| Businesses Displaced | 0 | 0 |
| Nonprofit Organizations Displaced | 0 | 0 |
| Households Temporarily Relocated, not Displaced | 0 | 0 |

| Households Displaced | Total | Minority Property Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Cost | 0 | 0 | 0 | 0 | 0 | 0 |

Table 10 – Relocation and Real Property Acquisition

## CR-20 - Affordable Housing 91.520(b)

Evaluation of the jurisdiction's progress in providing affordable housing, including the number and types of families served, the number of extremely low-income, low-income, moderate-income, and middle-income persons served.

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of Homeless households to be provided affordable housing units | 0 | 0 |
| Number of Non-Homeless households to be provided affordable housing units | 22 | 28 |
| Number of Special-Needs households to be provided affordable housing units | 0 | 0 |
| Total | 22 | 28 |

Table 11 – Number of Households

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of households supported through Rental Assistance | 0 | 0 |
| Number of households supported through The Production of New Units | 11 | 26 |
| Number of households supported through Rehab of Existing Units | 12 | 2 |
| Number of households supported through Acquisition of Existing Units | 0 | 0 |
| Total | 23 | 28 |

Table 12 – Number of Households Supported

Discuss the difference between goals and outcomes and problems encountered in meeting these goals.

The skyrocketing price of homes, high interest rates, as well as homes selling for well above asking price has made it difficult for first-time homebuyers to be able to purchase a house using our down-payment assistance program even with the change to the amount of funds the program can offer. We were however able to provide downpayment assistance to 4 First Time Homebuyers who purchased newly constructed units that were constructed by a non-profit developer. Most of our rehab is tied to our Lead grant from the Office of Healthy Homes & Lead Hazard Control. Staff has found getting the appropriate documentation needed for income certification of both owners and tenants challenging. This delays the approval process which in turn delays production of units. There were 2 vacant staff positions in the Housing Division in the Department. During the Program Year, we had 2 rental housing development projects that were completed and rented up.

Discuss how these outcomes will impact future annual action plans.

There should not be any impact on future Action plans.

Include the number of extremely low-income, low-income, and moderate-income persons served by each activity where information on income by family size is required to determine the eligibility of the activity.

| Number of Households Served | CDBG Actual | HOME Actual |  |
| --- | --- | --- | --- |
| Extremely Low-income | 60 | 15 |
| Low-income | 24 | 1 |
| Moderate-income | 4 | 10 |
| Total | 88 | 26 |

Table 13 – Number of Households Served

Narrative Information

## CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)

Evaluate the jurisdiction’s progress in meeting its specific objectives for reducing and ending homelessness through:

Reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs

The City of Lawrence is committed to increasing long-term housing stability and economic self-sufficiency of homeless and at-risk individuals and families. The City will utilize HOME and HOME-ARP funds to produce additional affordable rental units and have dedicated CDBG funds to support self-sufficiency and economic development.
  The Continuum of Care (CoC) uses a Coordinated Entry system and outreach teams to address the needs of homeless persons, with a special emphasis on unsheltered persons. Outreach teams respond to any report of an unsheltered family with children and locate an immediate placement in alternative housing settings.

In 2016, the City ordinance the Homelessness Initiatives Coordinator’s position, and hired a new staff person who sits within the Community Development Department. This position has been instrumental in providing and sharing resources with area providers through the Lawrence Mayor’s Health Task Force, a health disparities coalition that’s now officially under the umbrella of OPD, as well as through participation at local, regional, and statewide meetings. 
The Homelessness Initiatives Coordinator also works in close collaboration with the Lawrence Police Department, the Department of Public Works, and the Housing Department to respond to homeless encampments complaints by residents and local businesses, using this opportunity to learn more about homeless trends and offer services in an attempt to house unsheltered individuals. The Homelessness Initiatives Coordinator resigned mid-way through the year and the job remained vacant for the remainder of the program year.

Addressing the emergency shelter and transitional housing needs of homeless persons

The City is providing CDBG funds to Emmaus as part of their match for the Fresh Start project funded through the Continuum of Care Grant program. Fresh Start is a permanent supportive housing leasing program targeting 14 chronically homeless individuals with 4 slots set aside for veterans.
Lastly, the City has expanded and strengthened partnerships with the Executive Office of Housing and Livable Communities (EOHLC) in Boston which has led to increased collaboration and service coordination, capacity-building opportunities for area service providers, and support for expanded services to better address youth homelessness (ages 18—24). Referrals are made to local emergency shelters or to Greater Lawrence Community Action Council who has funds to place clients into temporary hotel stays. The City also places clients in hotels as funds are appropriated.

Helping low-income individuals and families avoid becoming homeless, especially extremely low-income individuals and families and those who are:  likely to become homeless after being discharged from publicly funded institutions and systems of care (such as health care facilities, mental health facilities, foster care and other youth facilities, and corrections programs and institutions);  and,  receiving assistance from public or private agencies that address housing, health, social services, employment, education, or youth needs

The City of Lawrence works with state and non-profit partners to ensure that people being discharged from publicly funded institutions are not discharged into homelessness. The Massachusetts Department of Mental Health (DMH) has designated several managers as representatives to the Balance of State CoC and the MA ICHH who work on discharge planning. These managers are responsible for working with and monitoring all CoC providers providing mental health services and they work on discharge planning for participants with severe and chronic mental health issues. Several of the providers are also active CoC members. DMH works with other state agencies and their providers around mental health issues, street outreach and discharge planning. DMH is the state agency responsible for ensuring persons being discharged from the public mental health (MH) system are not discharged into homelessness.

Helping homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness, facilitating access for homeless individuals and families to affordable housing units, and preventing individuals and families who were recently homeless from becoming homeless again

Lawrence is no longer its own CoC as it joined the Balance of State CoC several years ago and staff regularly participate in the Planning Group meeting that are held monthly.
  Staff from the Community Development Department interacts with the public seeking assistance with housing needs on an ongoing basis by providing referrals to appropriate local agencies and service providers. As part of the Balance of State CoC Planning Group, the City participates in the Continuum of Care Grant Program Application including the Ranking and Review of renewal applications which requires discussion of how the applications meet the needs and priorities of the CoC.
The Balance of State CoC launched a Coordinated Entry System for individuals and families and the City was an active participant in the creation of this system which will prioritize individuals with the greatest needs using a tool to determine vulnerability.Use of the Balance of State CoC coordinated entry system ensures that the most vulnerable chronic homeless individuals and families are prioritized and are more quickly and appropriately placed in permanent, sustainable housing settings.

## CR-30 - Public Housing 91.220(h); 91.320(j)

Actions taken to address the needs of public housing

The City of Lawrence has extremely limited resources to assist the Lawrence Housing Authority with its Capital Needs. The City has supported the LHA's efforts at the recapitalization and restructuring of its housing portfolio to accomplish needed capital projects and ensure long-term sustainability of the public housing stock. The City undertakes the required environmental review for the LHA’s HUD-funded capital projects.

Additionally, a member of the OPD/CDD staff is on the LHA eviction committee, and Lead abatement job training paid with the lead grant is offered to LHA residents.

Actions taken to encourage public housing residents to become more involved in management and participate in homeownership

Resident Councils regularly engage with management on facility needs, management policies, and/or security issues. The LHA and the City will continue to support resident engagement through support for public service programs which operate at LHA sites as well as through the recognition of Resident Organizations in the development of future plans.
 LHA identifies management initiatives in their plan for HUD.

Actions taken to provide assistance to troubled PHAs

The LHA is not troubled.

## CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)

Actions taken to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment. 91.220 (j); 91.320 (i)

The City has adopted several ordinances and strategies which encourage the development of new housing. In December 2024, we adopted an amendment to our zoning ordinance, establishing the requirements of Section 3A of GL 40A (MBTA Communities Law) which adopted a "by-right" requirement for new multi-family housing production.

We also amended one of our new Industrial Districts;  I-4 or Planned Industrial Development District, to require a 20% threshold for affordable housing as part of the permitting requirements.

We are also working on our fourth Smart Growth District or "40R" which allows permitting of multi-family homes, again "by-right".

Actions taken to address obstacles to meeting underserved needs.  91.220(k); 91.320(j)

Homeownership continues to be an underserved need and we continue to program HOME funds each year toward this. Additionally, given Lawrence’s high percentage of old housing stock, our CDBG funds serve as a match and complement our lead abatement program’s housing rehabilitation work.
The Homelessness Initiatives Coordinator continues to work closely with local government, area providers, and law enforcement to address issues faced by chronically homeless individuals. The Homelessness Initiatives Working Group under the City of Lawrence Mayor’s Health Task Force no longer exists. The work has been assumed by the Merrimack Valley Homelessness Group that is chaired by Dr. Ryan Dono of the Greater Lawrence Family Health Center.
 • Downpayment and closing cost assistance that allows low and moderate income buyers to buy a home;
• Rehabilitation support to “mom and pop” owners of two and three family stock, recognizing their role in providing affordable rental units;
• Utilization of tax-title and/or municipal properties to expand housing and economic opportunities designed to increase resident income

Actions taken to reduce lead-based paint hazards. 91.220(k); 91.320(j)

- Project management, technical assistance, and matching funds for Healthy Homes and Lead Hazard Control grants. The City has a Lead Hazard Reduction Grant with a Healthy Homes Supplement from the Office of Healthy Homes and Lead Hazard Control.

- Continued participation by the City in the State's Get the Lead Out program which provides the City with access to rehabilitation funding for lead-based paint removal through the local CDFI.

Actions taken to reduce the number of poverty-level families. 91.220(k); 91.320(j)

The City, primarily through the Mayor’s Health Task Force (MHTF), also participates in the GLFHC Social Determinants of Health working group, a collaboration between the local health clinic, Northeast Legal Aid, and the MHTF. This group is using an assessment tool as the gateway to assess for other socioeconomic needs of patients and to partner with community groups, as well as legal services to support those who are housing insecure. Through this collaboration, the group is about to launch a map layer that will show the correlation between food insecurity and incidences of chronic diseases which will serve as a tool for health prevention planning. 
The CDBG funding allocation to Emmaus supports permanent housing efforts paired with supportive services.

Actions taken to develop institutional structure. 91.220(k); 91.320(j)

The Office of Planning and Development (which includes the Community Development Department) will continue to engage other City departments and public-private partnerships, such as the Mayor's Health Task Force, in the implementation of the activities identified within the Annual Action Plan. Through enhanced coordination, the CDBG and HOME funded activities are an essential piece of larger community revitalization efforts.

Actions taken to enhance coordination between public and private housing and social service agencies. 91.220(k); 91.320(j)

- Convene Mayoral task forces on a number of important initiatives such as health and the provision of ESOL classes

- Participate in public-private partnerships such as the Lawrence Partnership.

- Encourage and support residential development of currently vacant space in the downtown area.

- Under the We Are Lawrence/Somos Lawrence (www.wearelawrence.org) platform, a large number of public and private organizations came together to better coordinate a response to the COVID-19 pandemic, creating a series of sub-groups with targeted focus on a variety of issues, including homelessness, food insecurity, financial & housing instability, education, outreach, and policy. Community Development staff has actively participated in these groups to help guide some of the decision-making.

Identify actions taken to overcome the effects of any impediments identified in the jurisdictions analysis of impediments to fair housing choice.  91.520(a)

The last analysis of impediments conducted by the City identified low income as the single most significant impediment. Our HOME-funded DP assistance program addresses this. Our goal is to conduct a new analysis of impediments.

## CR-40 - Monitoring 91.220 and 91.230

Describe the standards and procedures used to monitor activities carried out in furtherance of the plan and used to ensure long-term compliance with requirements of the programs involved, including minority business outreach and the comprehensive planning requirements

Citizen Participation Plan 91.105(d); 91.115(d)

Describe the efforts to provide citizens with reasonable notice and an opportunity to comment on performance reports.

The City of Lawrence places a legal notice in the Eagle Tribune, the local mainstream newspaper with the greatest circulation, about the availability of the CAPER for public comment. Hard copies are made available at the Office of Planning & Development, the City Clerk's office and the Lawrence Public Library. The CAPER is also uploaded to the City's website at https://www.cityoflawrence.com/715/HUD-CAPER .

## CR-45 - CDBG 91.520(c)

Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.

The City has been using a portion of its CDBG grant to make principal and interest payments on a Section 108 loan for the Gateway Parking. The last note was defeased in May 2025. No further payments will need to be made. The parking lot is complete along with an adjacent park. The Merrimack Valley Regional Transit Authority (MVRTA) is running the parking lot. It has been operating with a deficit since it opened and the MVRTA has not been able to make any payments to the City except for one time in 2012. The City has engaged an attorney to negotiate a new MOA that will remove the MVRTA, now called MeVa, and the City will take over operations of the parking lot.

Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants?

No

[BEDI grantees]  Describe accomplishments and program outcomes during the last year.

## CR-50 - HOME 24 CFR 91.520(d)

Include the results of on-site inspections of affordable rental housing assisted under the program to determine compliance with housing codes and other applicable regulations

Please list those projects that should have been inspected on-site this program year based upon the schedule in 24 CFR §92.504(d). Indicate which of these were inspected and a summary of issues that were detected during the inspection. For those that were not inspected, please indicate the reason and how you will remedy the situation.

The ten properties that were not inspected at due time is because of a combination of new and limited staff which created a complex situation that caused significant project delays. These factors lead to decreased productivity, knowledge gaps, and missed milestones. We will remedy the situation by scheduling these properties in the following 3-4 weeks to be up to date promptly.

Provide an assessment of the jurisdiction's affirmative marketing actions for HOME units. 24 CFR 91.520(e) and 24 CFR 92.351(a)

All HOME funded development projects have an affirmative marketing plan which OPD and EOHLC review.

Refer to IDIS reports to describe the amount and use of program income for projects, including the number of projects and owner and tenant characteristics

Describe other actions taken to foster and maintain affordable housing. 24 CFR 91.220(k) (STATES ONLY: Including the coordination of LIHTC with the development of affordable housing). 24 CFR 91.320(j)

HOME funds were committed to support Phase 2 of the Island Parkside housing development project, to create 40 new units of rental housing, for a total commitment of $700,000. The initial commitment was $400,000 but the cost of construction has skyrocketed and the developer requested an additional $300,000 that the Mayor approved.  A commitment of $400,000 in HOME funds was made to support a funding application for the development of 86 units of rental housing at the Stone Mill. Again, the cost of construction has skyrocketed and the developer requested an additional $100,000 that the Mayor approved. A second request for additional funding was received for $500,000. The Mayor awarded $350,000 bringing the total investment to $850,000. All of these projects have closed and are under or have completed construction. A request for funding for 150 rental units also located at the Marriner Mill building was made by another developer. A soft commitment of $850,000 has been made pending meeting the conditions set forth in the letter including completion of the environmental review which is underway. A request for funding for 98 rental units located at 59-71 Merrimack Street was made by another developer. A soft commitment of $1,000,000 has been made pending meeting the conditions set forth in the letter including completion of the environmental review which is underway.

## CR-55 - HOPWA 91.520(e)

Identify the number of individuals assisted and the types of assistance provided

Table for report on the one-year goals for the number of households provided housing through the use of HOPWA activities for: short-term rent, mortgage, and utility assistance payments to prevent homelessness of the individual or family; tenant-based rental assistance; and units provided in housing facilities developed, leased, or operated with HOPWA funds.

| Number of Households Served Through: | One-year Goal | Actual |
| --- | --- | --- |
| Short-term rent, mortgage, and utility assistance to prevent homelessness of the individual or family | 0 | 0 |
| Tenant-based rental assistance | 0 | 0 |
| Units provided in permanent housing facilities developed, leased, or operated with HOPWA funds | 0 | 0 |
| Units provided in transitional short-term housing facilities developed, leased, or operated with HOPWA funds | 0 | 0 |
| Total | 0 | 0 |

Table 14 – HOPWA Number of Households Served

Narrative

The City is not a HOPWA grantee.

## CR-58 – Section 3

Identify the number of individuals assisted and the types of assistance provided

| Total Labor Hours | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |
| Total Number of Activities | 1 | 1 | 0 | 0 | 0 |
| Total Labor Hours | 0 | 27,564 |  |  |  |
| Total Section 3 Worker Hours | 0 | 11,940 |  |  |  |
| Total Targeted Section 3 Worker Hours | 0 | 0 |  |  |  |

Table 15 – Total Labor Hours

| Qualitative Efforts - Number of Activities by Program | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |
| Outreach efforts to generate job applicants who are Public Housing Targeted Workers |  | 1 |  |  |  |
| Outreach efforts to generate job applicants who are Other Funding Targeted Workers. |  | 1 |  |  |  |
| Direct, on-the job training (including apprenticeships). |  |  |  |  |  |
| Indirect training such as arranging for, contracting for, or paying tuition for, off-site training. |  |  |  |  |  |
| Technical assistance to help Section 3 workers compete for jobs (e.g., resume assistance, coaching). |  |  |  |  |  |
| Outreach efforts to identify and secure bids from Section 3 business concerns. |  |  |  |  |  |
| Technical assistance to help Section 3 business concerns understand and bid on contracts. |  |  |  |  |  |
| Division of contracts into smaller jobs to facilitate participation by Section 3 business concerns. |  |  |  |  |  |
| Provided or connected residents with assistance in seeking employment including: drafting resumes,preparing for interviews, finding job opportunities, connecting residents to job placement services. |  |  |  |  |  |
| Held one or more job fairs. |  | 1 |  |  |  |
| Provided or connected residents with supportive services that can provide direct services or referrals. |  |  |  |  |  |
| Provided or connected residents with supportive services that provide one or more of the following: work readiness health screenings, interview clothing, uniforms, test fees, transportation. |  |  |  |  |  |
| Assisted residents with finding child care. |  |  |  |  |  |
| Assisted residents to apply for, or attend community college or a four year educational institution. |  |  |  |  |  |
| Assisted residents to apply for, or attend vocational/technical training. |  |  |  |  |  |
| Assisted residents to obtain financial literacy training and/or coaching. |  |  |  |  |  |
| Bonding assistance, guaranties, or other efforts to support viable bids from Section 3 business concerns. |  |  |  |  |  |
| Provided or connected residents with training on computer use or online technologies. |  |  |  |  |  |
| Promoting the use of a business registry designed to create opportunities for disadvantaged and small businesses. |  |  |  |  |  |
| Outreach, engagement, or referrals with the state one-stop system, as designed in Section 121(e)(2) of the Workforce Innovation and Opportunity Act. |  |  |  |  |  |
| Other. |  |  |  |  |  |

Table 16 – Qualitative Efforts - Number of Activities by Program

Narrative

Meeting the Section 3 goals has proved challenging. Many if not all of the contractors who bid on Section 3 jobs are fully staffed and from out of town. Very few have Lawrence residents on staff to help meet the Targeted Section 3 Worker hours. Also, many of them work on prevailing wage projects and therefore do not meet the income guidelines.